## Summary
Requirements Review — Authentication & User Profile Management
Gap analysis performed BEFORE test case creation / execution, based strictly on the Epic and User Stories text provided.
Total gaps | 40
By Priority | Count
High | 21
Medium | 14
Low | 5
By Type | Count
Ambiguity | 10
Missing Acceptance Criteria | 7
Missing Security Requirement | 6
Missing Validation | 4
Missing Business Rule | 4
Missing Requirement | 3
Missing Error Handling | 3
Dependency Gap | 2
Contradiction | 1
Top gaps that may block testing
• GAP-001 / GAP-002 — No defined response structure or status codes for any endpoint.
• GAP-010 / GAP-033 — No defined rule for role assignment at registration or role change later (matches a critical security finding found in execution).
• GAP-007 — No defined behavior for duplicate email registration.
• GAP-011 / GAP-014 / GAP-021 / GAP-029 — No explicit requirement that password/hash must never appear in any response (matches a confirmed password-exposure defect found in execution).
• GAP-020 — Direct contradiction between what Get Profile returns and what Update Profile allows changing.
• GAP-015 / GAP-027 / GAP-034 / GAP-037 — No defined status codes/messages for the most common failure paths.

## Requirements Gaps
ID | Epic | User Story | Type | Question / Gap | Raised By | Priority | Status | Owner / Assigned To | Date Raised | Clarification/Decision
GAP-001 | Authentication & User Profile Management | All User Stories (Cross-Cutting) | Missing Acceptance Criteria | What is the standard response envelope/structure (field names, success flag, error format) for every endpoint in this epic? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-002 | Authentication & User Profile Management | All User Stories (Cross-Cutting) | Missing Acceptance Criteria | What exact HTTP status code is expected for each success and each failure case on every endpoint (register, login, profile, update)? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-003 | Authentication & User Profile Management | All User Stories (Cross-Cutting) | Ambiguity | Should error messages be generic (e.g., "Invalid request") or field-specific (e.g., naming which field failed and why)? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-004 | Authentication & User Profile Management | Register User | Ambiguity | Of the five listed fields (email, password, fullName, phone, address), which are mandatory and which are optional? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-005 | Authentication & User Profile Management | Register User | Missing Validation | What is the required email format/pattern for registration? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-006 | Authentication & User Profile Management | Register User | Missing Validation | What is the minimum and maximum password length, and are there complexity rules (uppercase, number, special character)? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-007 | Authentication & User Profile Management | Register User | Missing Business Rule | Must the email be unique across all users? What status code/message is returned when registering with an already-used email? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-008 | Authentication & User Profile Management | Register User | Missing Validation | What format/length constraints apply to the phone field (digits only, country code, min/max length)? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-009 | Authentication & User Profile Management | Register User | Missing Validation | What are the length/character constraints for fullName and address? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-010 | Authentication & User Profile Management | Register User | Missing Business Rule | Can a role be supplied in the registration request, or is a role always assigned automatically? If automatic, what is the default role? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-011 | Authentication & User Profile Management | Register User | Missing Security Requirement | Does the "user details" returned in the registration success response ever include the password or password hash? Must this be explicitly excluded? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-012 | Authentication & User Profile Management | Register User | Ambiguity | Is the email treated as case-sensitive or case-insensitive for storage and uniqueness comparison? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-013 | Authentication & User Profile Management | Register User | Missing Requirement | Is an email verification/confirmation step required before the account can log in, or is the account active immediately after registration? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-014 | Authentication & User Profile Management | Login User | Missing Security Requirement | Does the "user info" returned on successful login ever include the password or password hash? Must this be explicitly excluded? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-015 | Authentication & User Profile Management | Login User | Missing Acceptance Criteria | What HTTP status code is returned for invalid credentials, and is the message identical for "wrong email" vs "wrong password" (to avoid revealing which one was wrong)? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-016 | Authentication & User Profile Management | Login User | Missing Security Requirement | Is there an account lockout or rate-limiting rule after repeated failed login attempts? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-017 | Authentication & User Profile Management | Login User | Ambiguity | Is the email comparison during login case-sensitive, consistent with the registration uniqueness rule (see GAP-012)? | QC | Low | Open | BA/PO/Developer | TBD | Pending
GAP-018 | Authentication & User Profile Management | Login User | Missing Business Rule | Can the same user hold multiple valid tokens at once (e.g., logged in on two devices simultaneously), or does a new login invalidate previous sessions? | QC | Low | Open | BA/PO/Developer | TBD | Pending
GAP-019 | Authentication & User Profile Management | Get Profile | Missing Error Handling | What specific status code/message is returned by this endpoint for a missing token, an invalid token, and an expired token respectively? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-020 | Authentication & User Profile Management | Get Profile | Contradiction | The AC states this endpoint returns only id, email, fullName, and role — excluding phone and address — yet Update Profile (US4) allows changing phone and address. Should GET /auth/profile also return phone and address so a user can view what they updated? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-021 | Authentication & User Profile Management | Get Profile | Missing Security Requirement | Must the response explicitly guarantee the password/password hash is never included? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-022 | Authentication & User Profile Management | Update Profile | Ambiguity | Is currentPassword required only when the password field is being changed, or on every profile update regardless of which fields are modified? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-023 | Authentication & User Profile Management | Update Profile | Missing Acceptance Criteria | Can the request update fields partially (e.g., only phone), or must the client resend the full profile object on every update? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-024 | Authentication & User Profile Management | Update Profile | Ambiguity | The AC lists name, phone, address, and password as updatable — email is not mentioned. Is email intentionally immutable via this endpoint? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-025 | Authentication & User Profile Management | Update Profile | Dependency Gap | Can a user's role be changed through this endpoint, or is role management handled by a separate, currently undefined endpoint/process (see GAP-010, GAP-033)? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-026 | Authentication & User Profile Management | Update Profile | Dependency Gap | Does the new password entered during an update have to satisfy the same validation rules defined for registration (see GAP-006)? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-027 | Authentication & User Profile Management | Update Profile | Missing Error Handling | What status code and message are returned when the supplied currentPassword does not match the account's actual password? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-028 | Authentication & User Profile Management | Update Profile | Missing Security Requirement | After a successful password change, does the user's existing JWT token remain valid until its natural 24-hour expiry, or is it invalidated immediately? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-029 | Authentication & User Profile Management | Update Profile | Missing Security Requirement | Does the "updated profile info" returned in the response ever include the password/password hash? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-030 | Authentication & User Profile Management | Role-Based Access Control | Ambiguity | What exact set of actions does "Admin can manage products/orders" cover — create, read, update, delete, or all of these? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-031 | Authentication & User Profile Management | Role-Based Access Control | Missing Acceptance Criteria | Does the Pharmacist role have any permissions beyond approving/rejecting prescriptions (e.g., viewing orders or products)? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-032 | Authentication & User Profile Management | Role-Based Access Control | Missing Acceptance Criteria | Does the Customer role have any interaction with prescriptions, or is that entirely outside this role's permissions? | QC | Low | Open | BA/PO/Developer | TBD | Pending
GAP-033 | Authentication & User Profile Management | Role-Based Access Control | Missing Business Rule | Who is authorized to assign or change a user's role after the account is created, and through which endpoint (depends on GAP-010, GAP-025)? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-034 | Authentication & User Profile Management | Role-Based Access Control | Missing Error Handling | What HTTP status code and message are returned when an authenticated user attempts an action their role does not permit? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-035 | Authentication & User Profile Management | Token Expiration & Security | Ambiguity | Is the 24-hour token expiration a fixed value or a configurable setting? | QC | Low | Open | BA/PO/Developer | TBD | Pending
GAP-036 | Authentication & User Profile Management | Token Expiration & Security | Ambiguity | Is the 24-hour expiration measured from the moment of token issuance, or is it extended/reset by ongoing user activity? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-037 | Authentication & User Profile Management | Token Expiration & Security | Missing Acceptance Criteria | What exact HTTP status code and message are returned for an expired token, and is this distinguishable from the message for an invalid/malformed token? | QC | High | Open | BA/PO/Developer | TBD | Pending
GAP-038 | Authentication & User Profile Management | Token Expiration & Security | Missing Requirement | Is there a token refresh mechanism, or must the user fully re-authenticate via login once the token expires? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-039 | Authentication & User Profile Management | Token Expiration & Security | Missing Requirement | Is there a logout or server-side token invalidation mechanism, given that JWTs are otherwise stateless and would remain valid until natural expiry? | QC | Medium | Open | BA/PO/Developer | TBD | Pending
GAP-040 | Authentication & User Profile Management | Token Expiration & Security | Ambiguity | The AC states passwords are "encrypted with BCrypt," but BCrypt is a one-way hashing algorithm, not reversible encryption. Please confirm the intended mechanism is hashing (not encryption/decryption). | QC | Low | Open | BA/PO/Developer | TBD | Pending